## Sheet1
Project Case Study Template
Client: | Morgan Sindall | Duration: | 10 Weeks
Project Title: | Saundersfoot Outfall Replacement | Project Value: | 650000
Requirement -
The existing 435m long Welsh Water Outfall running across Saundersfoot Beach in South West Wales had been exposed and hence damaged by the sea over the years. The damage meant that there was a requirement for it to be removed and replaced by a new 289m long 355mm OD HPPE SDR17 pipe.
Solution
Working as a sub-contractor for Morgan Sindall, on behalf of Welsh Water, TMS were awarded the contract to remove and replace the Welsh Water Outfall. Working around the challenging tidal conditions, TMS began by removing the existing pipeline, before replacing it with the new pipe in 25-40m sections. Three different design details were utilised throughout the installation, depending on ground conditions. In the upper beach zone, there were two design details used for shallow rock zones and deep rock zones. In areas classified as the shallow rock zone, the pipe was laid in the trench accompanied with concrete collars at 3.6m centres, and then back filled to match the existing beach level. In areas classified as the deep rock zone, the new pipe was laid to line and level before being covered in a 200mm concrete cap and then backfilled. In the lower beach zone, the pipe was laid with concrete collars at 6.6m centres, backfilled to the top of the collars and then covered with concrete mattresses to weigh the pipe down. The area was then backfilled. 30T Excavators were used throughout the installation, to excavate around the existing pipe, remove and load the old pipe and sheet pile foundations into dumpers for disposal, and lift and lower the new sections of pipe into position. The final stages of the project involved the installation of a bespoke diffusor to the end of the pipeline and the relocation of the existing marker buoy from the end of the existing pipeline to the end of the new one.
Photo's before & after